## Overview
Royal Cyber ¦ MetaFyAI + Commerce Tools — 6-Week Sales Plan
Cycle 2 · July 27 – September 4, 2026 · One salesperson (Ella) · Two motions · Owned by CMO Office
THE THROUGH-LINE
Ella runs pipeline execution for BOTH motions on one weekly rhythm. MetaFyAI is a VOLUME motion (trials → paid POCs → AE partnerships) anchored by the Chicago event Jul 30. Commerce Tools is a PARTNER motion (Ryan Hamer + Christian Schlaadt) with the Cornerstone Building Brands deal and a joint kickoff Jul 28. Content, technical demos, and executive relationships stay with Marketing, Practice, and Huzefa. Ella is the single owner for outbound, inbound follow-up, and deal progression.
⚠ TARGET CHECK: 12 MetaFyAI meetings + 4 CT meetings + 5 paid POCs + Cornerstone SOW (by Aug 21) + 4 CT-sourced opps. Two anchor commitments in Week 1 (Chicago event + CT kickoff) set the whole cycle — if either slips, escalate to Huzefa immediately.
WEEKLY ANCHOR MOMENTS (each week builds one lead-generating anchor, on top of the always-on rhythm)
# | Anchor | Why it's the anchor | Motion | Lead week
1 | Chicago event follow-up | Highest-leverage top-of-funnel moment of the cycle — 40+ live contacts primed for trial signup. | MetaFyAI | Wk 1
2 | commercetools kickoff + CT video engine | Launches the partner motion; Cornerstone status + weekly customer-story video distribution begins. | Commerce Tools | Wk 1
3 | Trial-to-POC conversion cadence | The core volume conversion — every trial user nudged Day-3 / Day-6 / Day-10 toward a paid POC. | MetaFyAI | Wk 2
4 | 'Win the AI Shelf' biweekly webinar | Structured-data / feed-quality proof play; strongest mid-funnel education asset. | MetaFyAI | Wk 3
5 | Cornerstone SOW close | The flagship CT deal milestone — SOW signed target, unlocks reference + 3 net-new opps. | Commerce Tools | Wk 4
6 | 'The Revenue Proof' webinar + joint CT webinar | ROI / attribution story that powers the end-of-cycle close on both motions. | Both | Wk 5
HOW TO READ THE WEEKLY TABS (each task is color-tagged by function)
| Sales | Outbound, inbound follow-up, meeting-booking, prospect research, CRM hygiene
| Marketing | Chicago event ops, videos, webinars, landing pages, content production
| Partnership | Ryan Hamer + Christian Schlaadt, CT weekly meeting, AE / partner intros
| Practice | Product / delivery — POC scoping demos, technical support
| Leadership | Escalations, blockers, exec sponsorship (Huzefa), weekly reporting
TOP BLOCKER TO RESOLVE (flagged for leadership)
Marketing turnaround. The weekly CT customer-story video must hit Ella's inbox Friday 9am for same-day distribution, and Chicago 3-track templates + biweekly webinar assets must land on time. Every slipped asset delays a distribution cycle. Ask: a standing weekly SLA on Ella's must-ship assets.

## Wk1 Jul27
WEEK 1 · Jul 27 – Aug 2
ANCHOR: Chicago event Jul 30 + commercetools kickoff Jul 28 — the two highest-leverage moments of the cycle.
Motions live this week: MetaFyAI (Chicago top-of-funnel) + Commerce Tools (partner launch)
Conversion path: Chicago contact → 24-hr 3-track email → 30-min demo on their SKUs → 7-day trial.
When | Team | Task | Owner | Deliverable / Output | Status
Mon | Sales | Draft 3-track Chicago follow-up email templates (engaged / attended / no-show) using M2 pattern. | Ella | 3 templates ready | Completed- https://rcyber-my.sharepoint.com/:w:/g/personal/ella_h_royalcyber_com/IQAUz_0ngZH_Rql9_Fte3a58AX2tHnk1gPwRzxi4-MKp2jE?e=HQmz2i
Mon | Sales | Prep CT kickoff: pull Cornerstone status, Marketplace listing screenshots, Ryan Hamer conversation log. | Ella | Kickoff pack ready | Completed; I am attaching a deck on how we have supported CBB. Looking forward to hearing their thoughts on why they are choosing to move to CT - https://rcyber-my.sharepoint.com/:p:/g/personal/ella_h_royalcyber_com/IQC-pBE1rVjGSbVxOfDh7svQAfT1KXtxx1R5mCnCLLpjddE?e=9n0p3E
Tue · 7pm CET | Partnership | commercetools kickoff — SUPPORT role (Christian Schlaadt, Andrii Chekanov, Alexandra). Take notes, don't lead. | Ella (CMO + Pampari lead) | Notes captured in CRM | Venkat has attended from the partnership side.
Wed | Sales | 40 MetaFyAI LinkedIn connection requests (M1 template) + attend Chicago dry-run to learn the demo flow. | Ella | 40 sent; demo memorized | 40 invites sent with personalized messaged about MetaFyAI to ecommerce managers from campaign. For the in-person event, Tejaswi will be presenting the demo. From a PowerPoint perspective, the deck has already been presented to management and received approval.
Thu | Marketing | ATTEND MetaFyAI Chicago event in person — capture business cards from every attendee, prime for trial signup. | Marketing (ops) + Ella | 40+ contacts logged | Ella prepared deck and full walkthrough. Development team (Jai & Tejaswi) have prepared full demo walkthrough.
Thu · eve | Sales | Log every Chicago contact into Dynamics before end of night. | Ella | All logged same-day | Completed - we have two new prospects.
Fri · 9am | Marketing | Week 1 CT customer-story video (CSA story) delivered to Ella's inbox. | Video Producer + Content | Video in hand | Video has been shared & sent to Sandeep for editing on Wednesday afternoon.
Fri | Sales | 24-hr Chicago follow-up: send 3-track emails to every attendee (M2 for engaged tier). | Ella | 40% engaged reply | Follow ups will be sent out on Monday to increase engagement. I have sent all prospcets Linkedin connections as well.
Fri | Marketing | Distribute Week 1 CT video to Ryan Hamer + 20 warm CT prospects (CT1 companion email). | Ella | Sent to 20+ | Waiting on video to be completed by Sandeep - will not be completed until Tuesday of next week. Once done I can start outreach to relevant industries and contacts (AI readiness)
Fri | Leadership | Send first Weekly Sales Report to Huzefa (meetings / POCs / CT wins / blockers / next-week top 3). | Ella → Huzefa | Report sent | Shared via video. Customer calls - Hangovr, Fellers (PIM), Caroma. Partnership - Venkat's connect, Lunch with Commercetools Partnership team. No POCs for week one.

## Wk2 Aug3
WEEK 2 · Aug 3 – Aug 9
ANCHOR: Post-Chicago conversion + first Ryan Hamer sync + first CT weekly meeting.
Motions live this week: MetaFyAI (trial conversion) + Commerce Tools (partner sync)
Conversion path: Chicago engaged tier → booked demo → trial provisioned → Day-3 nudge scheduled.
When | Team | Task | Owner | Deliverable / Output | Status
Mon | Sales | 10 personalized 'here's what you saw + book a demo' emails to top-engagement Chicago tier. | Ella | 10 sent, 3+ bookings | All prospects have been contacted via email & Linkedin. One meeting set up with agency.
Tue | Partnership | First Ryan Hamer sync (CT2 agenda): Cornerstone status + 3 net-new named accounts to jointly pursue. | Ella + Ryan Hamer | 3 accounts activated | Ryan has been unresponsive - however we have a meeting with Rachel Poole this week and we will connect with her in person the following. Wes and previous AEs have been followed up by team as well. I have been given Jessica Ralstons full customer list which we are cross checking to see alignment.
Tue | Sales | Qualify new CT prospects (Abbott, Darden, Levi Strauss) — add fits to the Ryan sync list. | Ella | Prospects qualified | I am proactively doing outreach for Darden, Levi, and Abbott, no responses yet. We had one lady sign up for the MetaFy event last week - I am working on a time with her too.
Tue | Sales | Launch "Is Your Commerce Stack Ready for What's Next?"(Commercetools) "SEO got here. AEO gets you found next"(MetaFy) | Ella | Launched | 32,000+ contacts on SAP Commerce. CTA included a Commerce Readiness Assestment. 40,000+ included for MetaFyAI
Wed | Sales | 40 MetaFyAI LinkedIn requests, prioritize A&F-adjacent commerce brands. | Ella | 40 sent | 40 requests sent each with a note on AI discovery. I also sent and additional 40 to promote our webinar next week.
Wed | Marketing | Distribute Week 2 CT video + Marketplace listing v2 announcement to warm CT prospects. | Ella | Sent | The video from last Wednesday is still delayed on Sandeep's end. As of Friday, video is still pending from last week.
Thu | Partnership | Weekly commercetools + RC sales meeting — attend with written status. | Ella (Vaibhav owns) | Attended, status logged | Completed.
Thu | Marketing | Post-Chicago debrief with Marketing — log trial-to-demo conversions. | Marketing + Ella | Conversions logged | So far this week we have recieved one meeting from the event.
Thu | Practice | Day-3 / Day-6 trial nudges (M3): every trial user gets a scoping-call proposal. | Ella (Practice on call) | Nudges sent | All previous prospects have been contacted. We have new interest from Kellanova and Kellog brands so I will work to set those meetings up for the coming weeks.
Fri | Leadership | KILL-CRITERIA CHECK #1 — Chicago reply rate + Ryan sync outcome. Weekly Report to Huzefa. | Ella → Huzefa | Pass or escalate | Customer calls - A&F, Balsam Brands, Sovereign Brands, ResultFirst (Partnership)

## Wk3 Aug10
WEEK 3 · Aug 10 – Aug 16
ANCHOR: 'Win the AI Shelf' biweekly webinar (Aug 12) + A&F POC scope + Cornerstone SOW push.
Motions live this week: MetaFyAI (enterprise scope + webinar) + Commerce Tools (SOW advance)
Conversion path: Webinar Q&A lead → 24-hr follow-up → demo on their SKUs → paid POC scope.
When | Team | Task | Owner | Deliverable / Output | Status
Mon | Sales | A&F next step — propose Brand POC scope (M5). Coordinate wording with Murtuza + Huzefa. | Ella + Murtuza | Scope sent | Call has been set up for August 25th
Tue | Partnership | Ryan Hamer sync #2: Cornerstone SOW status + 2 more accounts. | Ella + Ryan Hamer | Cornerstone advanced | We sent over the joim account list to CT team to establish a joint customer story, recieved the full account list from Alexandra. Since we have the list we will rengage with prospects around our commerce capabilities and MetaFy.
Wed | Marketing | MetaFyAI biweekly webinar 'Win the AI Shelf' — attend live, capture Q&A leads, 24-hr follow-up. | CMO+Product host / Ella captures | 10+ Q&A leads | 54 sign ups and 27 attendees
Wed | Marketing | Distribute Week 3 CT video (migration story). | Ella | Sent | Video is still pending - not sure if this is possible to do every week. We will proceed with doing podcasts/discussions.
Thu | Partnership | Weekly commercetools + RC meeting. | Ella (Vaibhav owns) | Attended | Vaibhav had a conflict. We connected on Friday.
Thu | Sales | Named-account coverage check — 70% touched by end of this week; chase any untouched. | Ella | 70% coverage | 9 Meetings (For reconnects - Harman, ANF, RAC, GWA, Mars)
Fri | Leadership | Weekly wrap + newsletter distribution. Report to Huzefa. | Ella → Huzefa | Sent | Mars (Kind Snacks), Harman, RAC

## Wk4 Aug17
WEEK 4 · Aug 17 – Aug 23
ANCHOR: Mid-cycle review + Cornerstone SOW target (Aug 21) + MetaFyAI partner wave.
Motions live this week: Commerce Tools (SOW close) + MetaFyAI (partner intros + POC push)
Conversion path: Cornerstone technical walkthrough → SOW sign-off; trial Day-14+ → POC decision.
When | Team | Task | Owner | Deliverable / Output | Status
Mon | Leadership | MID-CYCLE PIPELINE REVIEW with Huzefa — on the 12-meeting base? Which motion under-delivering? | Ella + Huzefa | Report + corrective plan | 9 meetings
Tue | Partnership | Ryan Hamer sync #3 — TARGET: Cornerstone SOW signed by end of week. | Ella + Ryan Hamer | SOW on track | Met with Alexandra and dicussed the customers we can do a joint story with, Shoptalk event
Wed | Partnership | 5 MetaFyAI partner intros scheduled (leverage Vijay Yadav's pipeline). | Ella + Vijay Yadav | 5 intros | ResultFirst, DS&P Agency, VaynerMedia (waiting on Vijay's updates)
Wed | Marketing | Distribute Podcast Video for MetaFyAI | Ella | Posted | Shared on MetaFy and Royal Cyber Linkedin Page
Wed | Sales | Cornerstone weekly nudge (CT3): offer Mahaveer technical walkthrough with two time windows. | Ella | Walkthrough booked | Not in the loop on this progress.
Thu | Partnership | Weekly commercetools + RC meeting. | Ella (Vaibhav owns) | Attended | Connected
Thu | Practice | Trial-to-POC push: any trial user Day-14+ not converted — Ella + Practice Lead close call. | Ella runs / Practice demos | 3+ POC decisions | In discussion for free trial - Connor, HANGOVR-180,
Fri | Partnership | CORNERSTONE SOW TARGET — signed today. Lamiaa confirms, Ella logs. Weekly Report. | Ella + Lamiaa + Mahaveer | SOW signed | Meetings - HANGOVR-180, Rock the Shot, Kellanova, EPCM Global, Connor

## Wk5 Aug24
WEEK 5 · Aug 24 – Aug 30
ANCHOR: 'The Revenue Proof' webinar (Aug 26) + joint commercetools + RC webinar (Aug 27) + close push.
Motions live this week: MetaFyAI (close push + webinar) + Commerce Tools (joint webinar + 2 new opps)
Conversion path: Trial end-of-trial ask → paid-POC signature; joint webinar reg → CT discovery.
When | Team | Task | Owner | Deliverable / Output | Status
Mon | Sales | Final meeting-ask wave to all MetaFyAI trial users approaching end-of-trial. | Ella | Wave sent
Tue | Partnership | Ryan Hamer sync #4 — focus: 2 new opportunities post-Cornerstone. | Ella + Ryan Hamer | 2 opps opened
Wed | Marketing | MetaFyAI biweekly webinar 'The Revenue Proof' — attend, capture leads, 24-hr follow-up. | CMO+Product host / Ella captures | 10+ leads | Moved to the following week because of time.
Wed | Marketing | Distribute Week 5 CT video (grocery / frozen story). | Ella | Sent | Will Run podcast
Thu | Partnership | JOINT commercetools + RC webinar (co-hosted w/ Christian Schlaadt). Ella pre-invites her + Ryan's named accounts. | Ella + CMO / Christian | 150+ reg / 60+ live
Thu | Sales | Named-account coverage check — 100% touched by end of this week. | Ella | 100% coverage
Fri | Practice | Weekly wrap. Trial users at Day-7 — Practice Lead conducts paid-POC scoping calls; Ella coordinates. | Practice Lead / Ella | POCs scoped
Fri | Leadership | Weekly Report to Huzefa. | Ella → Huzefa | Sent | Kellogg, True Religion, ANF, CBB, Sharp USA, Rock the Shot

## Wk6 Aug31
WEEK 6 · Aug 31 – Sep 4
ANCHOR: Cycle 2 wrap + Ryan Hamer QBR + Elevate 2026 planning start.
Motions live this week: MetaFyAI (final close block) + Commerce Tools (QBR + Elevate prep)
Conversion path: Top-20 engagement block → booked meetings; QBR → Cycle 3 priorities.
When | Team | Task | Owner | Deliverable / Output | Status
Mon | Sales | Final push call block: top 20 prospects by engagement score. Book meetings. | Ella | 20 calls / 3+ mtgs
Tue | Partnership | Ryan Hamer QBR — Cycle 2 review: wins, losses, Cycle 3 priorities. | Ella + Ryan Hamer | QBR done
Wed | Partnership | Elevate 2026 planning kickoff — pull target-attendee list + prior-year contact roster. | Ella + Pampari | Attendee list drafted
Wed | Marketing | Distribute Week 6 CT video (final). | Ella | Sent
Thu | Leadership | 6-Week Cycle 2 Review meeting — Huzefa + Pampari Venkat + Christian Schlaadt. | Ella + Huzefa + Pampari | Review deck presented
Fri | Leadership | Cycle wrap: final Weekly Report + Cycle 2 summary + Cycle 3 first-week draft plan. | Ella → Huzefa | Summary sent

## Always-On Rhythm
ALWAYS-ON WEEKLY RHYTHM — the backbone that runs every week of the cycle
This runs underneath the weekly anchors. Same cadence Mon–Fri, every week, regardless of that week's anchor. ~35 hrs of focused execution.
Day | Team | Ritual | Owner
Mon | Sales | Trial-signup follow-ups — all users hitting Day-3 or Day-6; send scoping-call proposal (M3). | Ella
Tue | Partnership | Ryan Hamer 30-min sync — NON-NEGOTIABLE. Cornerstone + 3 named accounts + this week's CT video preview. | Ella + Ryan Hamer
Wed | Marketing | MetaFyAI outbound — 40 LinkedIn connection requests + Wave-1 accept follow-ups (M1). | Ella
Thu | Partnership | Weekly commercetools + RC meeting — always attend with written status (Vaibhav owns). | Ella / Vaibhav
Thu | Practice | Trial-to-POC conversion calls — Ella runs discovery, Practice Lead demos. | Ella + Practice
Fri | Marketing | CT customer-story video distribution — Friday 9am video → companion emails to Ryan + warm CT prospects (CT1). | Ella
Fri | Leadership | Weekly Sales Report to Huzefa (5 lines) + CRM hygiene: every touch logged same day. | Ella → Huzefa
NON-NEGOTIABLES EVERY WEEK (don't skip — these anchor the rhythm)
1. Ryan Hamer sync Tuesday morning — never skipped. If Ryan is unavailable, reschedule to Wed and rearrange the week.
2. Thursday commercetools + RC weekly meeting — always attend, always come with a written status.
3. Friday Weekly Sales Report to Huzefa — 5 lines: meetings booked, POCs advanced, CT wins, blockers, next week's top 3.
4. CRM hygiene — every touch, every reply, every next step logged same day. Rolls up to Irfan Monday morning.
5. Trial cadence — every trial user gets Day-3 nudge, Day-6 scope-call setup, Day-10 close ask. No trial goes cold.

## Event Prep
EVENT PREP · Chicago event (Jul 30) + commercetools kickoff (Jul 28) + joint CT webinar (Aug 27)
Cross-cutting workstream. Week 1 is the anchor — Chicago + CT kickoff land in the same week and set the cycle. The joint CT webinar in Wk5 is the second major event moment.
Workstream | Team | Task | Owner | Target wk
Chicago follow-up | Sales | 3-track email templates (engaged / attended / no-show) built before the event; 24-hr sweep ready. | Ella | Wk1
Chicago capture | Marketing | Onsite business-card capture + trial-signup priming for all 40+ attendees; same-night CRM logging. | Marketing + Ella | Wk1
CT kickoff prep | Sales | Cornerstone status + Marketplace listing screenshots + Ryan Hamer log assembled for the Jul 28 kickoff. | Ella | Wk1
CT kickoff | Partnership | Support role at commercetools kickoff (Christian + Andrii + Alexandra) — notes, not lead. | Ella (CMO+Pampari lead) | Wk1
Video engine | Marketing | 6 weekly CT customer-story videos delivered Friday 9am for same-day distribution to 20+ each. | Video + Content | Wk1–6
Biweekly webinars | Marketing | 'Win the AI Shelf' (Aug 12) + 'The Revenue Proof' (Aug 26) — Ella attends live, captures Q&A leads. | CMO + Product / Ella | Wk3, Wk5
Joint CT webinar | Partnership | Co-hosted commercetools + RC webinar Aug 27 — Ella pre-invites her + Ryan's named accounts. | Ella + Christian | Wk5
Partnership kit | Partnership | 3 top partners/week get a 1:1 CMO video from Huzefa; Ella distributes + logs (M4). | Ella / Partner Mktg | Wk3–6
Elevate 2026 | Partnership | Pull target-attendee list + prior-year contact roster to seed Cycle 3 pipeline. | Ella + Pampari | Wk6
Cadence | Leadership | Standing weekly review with Huzefa; mid-cycle checkpoint Wk4; kill-criteria check Wk2. | Ella | Wk1→wrap

## Research,Campaign & Talk Tracks
RESEARCH-BACKED TALK TRACKS — weekly content topic + messaging spine (AEO / GEO, verified Jul 2026)
One certified content topic per week, each anchored to a live AEO / GEO conversation (the Profound / Evertune / GEO crowd) and mapped to MetaFyAI's value prop. Marketing/Content produces the asset; Ella distributes and captures leads. |  | Campaign Updates/Logistics/Outcome
Wk1 — Is AI recommending your products, or your competitor's? | TREND: 393% YoY growth in AI-referral traffic to US retail (Adobe Q1'26); 61% of consumers now use AI tools for shopping research. Most brands can't tell whether ChatGPT / Perplexity / Gemini surface them. ANGLE: MetaFyAI's core hook — run it live on their own SKUs + top 3 competitors. FORMAT: carousel + 60-sec demo clip. Perfect Chicago lead magnet. | Meetings - 2 - 308 net-new eCommerce & Retail prospects ¦ 3-touch outreach campaign (Tue/Thu/Mon) + LinkedIn follow-up to engaged prospects ¦ Reached 91.5% of contacts ¦ 11.9% engagement rate
Wk2 — Share of Voice beats rankings | TREND: GEO success is measured in Share of Voice and Entity Authority, not blue-link positions; Gartner projects a 25% decline in traditional search. ANGLE: MetaFyAI quantifies share-of-voice per category and per competitor — the scorecard exec teams now demand alongside web traffic. FORMAT: blog + LinkedIn post. | 30,000 SAP Commerce contacts ¦ 3-touch outreach campaign (Tue/Thu/Mon) + LinkedIn follow-up to engaged prospects ¦ Reached 93.3% of contacts ¦ 7.3% engagement rate
Wk3 — Win the AI Shelf: structured data that gets you cited | TREND: ~83% of ChatGPT's shopping carousel pulls from Google Shopping feeds; 95%+ attribute completion on top SKUs is the entry ticket. Feed quality, not webpages, decides who AI recommends. ANGLE: MetaFyAI audits feed completeness and flags the exact attribute gaps costing citations. FORMAT: biweekly webinar (same title, Aug 12) + companion guide. | 54 sign ups for webinar - 27 shows. 2 leads generated this week.
Wk4 — Agentic commerce: can an AI agent even read your catalog? | TREND: Shopify AI-attributed orders grew 11x YoY (Jan'25→Jan'26); Gartner sees 25% of enterprise purchases AI-mediated by end of 2026; MCP-queryable product data wins. ANGLE: MetaFyAI as future-proofing — visibility today plus agent-readiness for zero-click / agentic checkout. Enterprise (A&F) angle. FORMAT: thought-leadership article. | Free trial Discussion with Connor, Rock the Shot, HANGOVR-180
Wk5 — The Revenue Proof: turning AI visibility into attributed sales | TREND: AI-referred shoppers convert at ~4.4x traditional organic (McKinsey); 2026 is the 'forcing mechanism' year — boards want attributed outcomes, not experiments. ANGLE: moves MetaFyAI from dashboard to ROI story — visibility lift → attributed sessions → conversion. FORMAT: biweekly webinar (same title, Aug 26) + case-study one-pager. Powers the close.
Wk6 — AI visibility in 2027: what the data says brands should do now | TREND: the category exploded from a handful of tools in 2024 to 15+ serious platforms in 2026 (Profound, Evertune, etc.); buyers now ask for next year's playbook. ANGLE: cycle-closing authority piece synthesizing the 6-week learnings into a forward POV — seeds Cycle 3 + Elevate 2026. FORMAT: recap report + Elevate teaser.
Commerce Tools spine (all weeks) | The Lamiaa pattern that works: 'We built a Customer Service Accelerator — plug-and-play, lives inside the commercetools merchant center. Brands like Mars and GSM already use it.' 60-sec video + CT1 companion email every Friday. Cornerstone: keep moving weekly, SOW target Aug 21, escalate to Lamiaa if silent 5+ days.
Sources (verified Jul 2026) | AI-referral traffic & attribution: Adobe Analytics Q1'26; AI-shopping conversion: McKinsey / BCG consumer surveys; feed dependency: ChatGPT shopping-carousel reporting; agentic adoption: Gartner + Shopify AI-order data; tooling landscape: Profound, Evertune, and AI-visibility category reviews circulating Jun–Jul 2026. Fact-check each stat against a current source before publishing.